Training and Development · E-R4

# Issue 3 Publication Readiness Register

Every item affecting publication of the Issue 3 courses, classified, with action and owner.

| Audience | Provincial Mentoring Team |
| --- | --- |
| Issue | Issue 1, November 2026 |
| Status | For Provincial review |

# About this register

This register lists every item that affects publication of the eleven Issue 3 courses, drawn from the lead editor's decisions, the writers' notes, the two QA reads, the facts register and the final course data. Each item has exactly one classification:

Must resolve before publication: the course should not go live until this is done.

Requires Provincial confirmation: the course carries a reasonable interim wording, but the Province must confirm or decide; some answers will need a small edit.

Editorial recommendation: an improvement that does not block publication.

Suitable for publication: checked and ready; listed so the evidence is on record.

| Classification | Items |
| --- | --- |
| Must resolve before publication | 5 |
| Requires Provincial confirmation | 25 |
| Editorial recommendation | 10 |
| Suitable for publication | 8 |
| Total | 48 |

# Must resolve before publication

| No. | Course(s) | Item | Classification | Why | Action and owner |
| --- | --- | --- | --- | --- | --- |
| 1 | E7f | Named Provincial safeguarding contact and policy (5.1; final Q9) | Must resolve before publication | Safety-critical. No policy or named contact is in the supplied documents; the course says 'the Provincial safeguarding contact' without naming it | Confirm the role, how to reach it and the policy, and whether to print local authority safeguarding numbers; then name it in 5.1 and Q9. Provincial Grand Secretary, with the Provincial Grand Almoner; lead editor. |
| 2 | E1, E2, E6 | Hub importer: load Issue 3 as a new version of an existing course | Must resolve before publication | The import script skips any course whose slug already exists, and versioning is not supported; E1, E2 and E6 already exist in the Hub | Add course versioning to the importer, then load E1, E2 and E6 as new versions and the eight E7 courses as new courses. Hub developer. |
| 3 | All | Hub importer: JSON loader | Must resolve before publication | The import script reads TypeScript course files only; Issue 3 is held as Course data/*.json | Add a loader for Course data/*.json. Hub developer. |
| 4 | All | Hub importer: read each lesson's required field | Must resolve before publication | The importer sets required: true on every lesson, so optional activities would block completion | Read the lesson's required field. Hub developer. |
| 5 | E7f; safety lines in E1, E2, E7a | Recheck nhs.uk urgent mental health guidance | Must resolve before publication | The nhs.uk 'Where to get urgent help for mental health' page was past its April 2026 review date when QA checked it | Recheck 999 and NHS 111 wording against the live page just before publication. Lead editor. |

# Requires Provincial confirmation

| No. | Course(s) | Item | Classification | Why | Action and owner |
| --- | --- | --- | --- | --- | --- |
| 6 | All | Provincial titles | Requires Provincial confirmation | Issue 3 uses Provincial Mentor, Deputy and Assistant Provincial Mentor as the brief asked; A3 canon and the July 2026 log use Provincial Grand Mentor titles. The copyright line follows Issue 3 | Confirm the titles. If canon titles are kept, find-and-replace in the eleven data files and the builder's COPYRIGHT_HOLDER. Provincial Mentor; lead editor. |
| 7 | E1 | The Charge (5.4), awaiting approval as canon, and its Issue 3 edits | Requires Provincial confirmation | Edits made: sign-off 'Provincial Mentor'; 'Why aren't you attending?'; priorities line; dashes removed. QA flags 'no one's absence goes unnoticed', 'navigates an unfamiliar world' and 'keep men the calendar would have lost' | Approve the Charge with or without the edits, and decide on the three phrases. Provincial Mentor. |
| 8 | E7f, E2 | MCF email and name | Requires Provincial confirmation | help@mcf.org.uk could not be confirmed and is not printed. E2 says 'Masonic Charitable Foundation'; E7f adds 'now operating as the Freemasons' Charity' | Confirm whether an email should be printed and the name to use. Provincial Grand Almoner. |
| 9 | E1, E2 | Monthly mentoring call details | Requires Provincial confirmation | First Tuesday, 7pm, Teams, from B1 Issue 2. E1 says it is open to Lodge Mentors and Personal Mentors; E2 says 'open to all Personal Mentors' | Confirm day, time, platform and audience at each issue. Deputy Provincial Mentor. |
| 10 | E1, E6, E7b, E7e | Same-day resignation notice to the Lodge Mentor (A05) | Requires Provincial confirmation | A Hertfordshire standard, not UGLE's. Teaching text says 'promptly'; E7e final Q6's correct answer still says 'in Hertfordshire, the Lodge Mentor' | Confirm the standard; if it is not adopted, edit E7e Q6. Provincial Grand Secretary. |
| 11 | E1, E2, E6, E7e | Two-missed-meetings wording (D10) | Requires Provincial confirmation | Courses use UGLE's 'with or without an apology', framed as a friendly habit; drafts said 'without a word' | Confirm the Province adopts UGLE's wording. Provincial Mentor. |
| 12 | E7a, E7b, E7c, E7e, E7f | A3 section 7 data rules still draft | Requires Provincial confirmation | Records guidance follows the draft baseline: retention 'a set period', twelve-month closure, member-held Plan (PLAN-7), whether Masonic membership is sensitive data | Sign off A3 section 7; lead editor then rechecks E7a 6.2, E7b 5.1 and E7c 6.1. Provincial Mentor, with the Province's data lead. |
| 13 | E7g | Non-Mason helper when learning ritual | Requires Provincial confirmation | UGLE allows a non-Mason to hold the book; A3 s5 forbids exposure to signs, tokens or words. Course prefers a Brother. Also whether to repeat UGLE's advice to record the ritual | Decide whether non-Mason helpers are acceptable; if not, change 4.2 callout, 4.3 step k2 and final Q4. Provincial Mentor. |
| 14 | E1, E6, E7e | Hermes Almoner alert (D11) | Requires Provincial confirmation | Courses say UGLE says Hermes will notify the Almoner where attendance is recorded; not confirmed as live in Hertfordshire | Confirm the feature is live and depends on the Secretary recording attendance. Provincial Grand Secretary. |
| 15 | E7e, E7c | Migration ownership (A13) | Requires Provincial confirmation | E7e 6.1 and final Q11 say the Provincial Office starts migration; unconfirmed as current procedure; E7c 4.2 ending kept general | Confirm who triggers migration and the current Hermes process. Provincial Grand Secretary. |
| 16 | E7c | Board of General Purposes tenure recommendation source (B15) | Requires Provincial confirmation | Only MetGL's report of the five-years, seven-at-the-outside recommendation was found; E7c 2.2 and Q10 attribute it to MetGL | Obtain the original BGP paper or accept the attributed wording. Provincial Grand Secretary. |
| 17 | E6, E7c | Dispensation fee (B05) | Requires Provincial confirmation | E6 6.1 prints 'the Handbook currently gives £12'; E7c says only 'a fee applies' | Confirm the fee at each issue. Provincial Grand Secretary. |
| 18 | E1, E2, E7b, E7d | Contact-timing standard after Initiation (LMG-8, PLAN-6) | Requires Provincial confirmation | Courses use 'before the next Lodge meeting', with UGLE's 'within a week or so' (E7d) and 'ideally within a week or two' (E2) | Settle the standard; update the four courses. Provincial Mentor. |
| 19 | E1, E6, E7e | Year after the Chair phrasing (D03) | Requires Provincial confirmation | No figures exist. E6 and E7e say 'Hertfordshire treats it as a second risk window'; E1 says 'a time to keep in touch' | Confirm the phrasing. Provincial Mentor. |
| 20 | E6 | Quorum of five and etiquette timings (B08, B14) | Requires Provincial confirmation | Quorum cited to the Secretaries' Handbook because Rule 119 does not state it; speech and Committee timings had no source and are now unnumbered suggestions | Give the constitutional source for the quorum; confirm the suggestions are acceptable. Provincial Grand Secretary. |
| 21 | E7f | Provincial Grand Almoner contact route and MHFA funding (F13) | Requires Provincial confirmation | Course says 'through the Provincial website or the Provincial Office'; MHFA funding is undecided | Confirm the route and whether the Province will fund MHFA courses. Provincial Grand Almoner. |
| 22 | E7h | Royal Arch Representative expectation and contact route (C06) | Requires Provincial confirmation | Course says every Lodge should have one, an appointment, not a Rule 104 office, and points to the Provincial Office. Building Together calls it a 'non-collared office'; 'four bridging points' language dropped | Confirm the expectation, contact route and preferred wording. Provincial Mentor. |
| 23 | E7h | Principle tag changed from Enlighten to Guide | Requires Provincial confirmation | Lead editor's judgement: the course is about accurate, timely information | Confirm or revert. Provincial Mentor. |
| 24 | E6 | Pass mark raised from 70% to 75% | Requires Provincial confirmation | No reason for 70% was found; the assessment is now judgement-based like the other courses | Confirm. Provincial Mentor. |
| 25 | E7g | Provincial events for new Brethren (A2 s8) | Requires Provincial confirmation | 5.1 refers to them 'where they are running'; not confirmed that they are | Confirm whether they run. Provincial Mentor. |
| 26 | E7d | Personal Mentor named at ballot (B19); partners' guide | Requires Provincial confirmation | Hertfordshire practice with no external source; a 'For Partners and Families' guide was not found in the library | Confirm the practice in B1; name the guide in 3.1 if it exists. Provincial Mentor. |
| 27 | E7b | What Lodge Mentors report to their Assistant Provincial Mentor | Requires Provincial confirmation | Issue 1 said 'quarterly return'; A2 sets quarterly returns for Assistant Mentors only; B1 mentions 'your quarterly picture' | Confirm what, if anything, Lodge Mentors submit. Provincial Mentor. |
| 28 | E2 | DAWG membership and published tools | Requires Provincial confirmation | E2 says 'ask your Lodge Mentor' to join DAWG; B2 Personal Mentor's Guide and D3 Stage Checklists are drafts | Confirm who adds Personal Mentors to DAWG and that B2 and D3 are issued. Provincial Mentor. |
| 29 | E2, E7d | Solomon material for Entered Apprentices (E08) | Requires Provincial confirmation | Not checked inside Solomon (login needed); courses refer to it generally | Check inside Solomon. Provincial Mentoring Team. |
| 30 | E7h | Building Together sources and Provincial Grand Chapter name | Requires Provincial confirmation | Practical lesson uses September 2025 conference slides; the published thread was not checked | Check the published thread and confirm the preferred name. Provincial Mentor. |

# Editorial recommendation

| No. | Course(s) | Item | Classification | Why | Action and owner |
| --- | --- | --- | --- | --- | --- |
| 31 | A2, B1, B2, B6, D4 | Library documents out of step with the courses | Editorial recommendation | A2 principle order (PMF-1), 'demonstrably', 'before joining other orders', Archway; B1 and B2 welfare to both Almoner and Lodge Mentor; B6 and D4 Rule 183 Lodge vote and 'one in three recovered'; B6 'national research' | Correct the documents; restore D4 to the E1 and E2 resource lists once corrected. Provincial Mentor. |
| 32 | Secretaries' Handbook | Handbook errors | Editorial recommendation | Pre-2020 Rule 127 text; quorum attributed to Rule 119; Rule 183 should lead with the Hertfordshire version; footers read May 2025 | Correct at next revision. Provincial Grand Secretary. |
| 33 | E7a to E7h | No 'specialist' level in the Hub | Editorial recommendation | The Hub ignores tier, so the catalogue shows E7 courses as Optional (E7f Recommended); code, issue, audienceText, completion, changeSummary and devNotes are also ignored (harmless) | Consider adding a specialist tier to the catalogue. Hub developer. |
| 34 | All | Hub docx export pass-mark text | Editorial recommendation | The Hub's export prints 'pass mark course default%' when a quiz has no pass mark; the Issue 3 builder prints the course pass mark | Fix the Hub exporter. Hub developer. |
| 35 | E1 | Principles block in 2.1 | Editorial recommendation | The only principles block in the collection. In the Hub it shows the Hub's own short definitions, which differ from the A1 text quoted verbatim straight after; the Word draft prints it as a 'Graphic:' placeholder. No other graphic placeholders remain (E7a's was removed) | Align the Hub's principle texts with A1, or drop the block from E1 2.1. Hub developer, with the Provincial Mentor. |
| 36 | E7a | Cross-reference to Helping Brethren Learn | Editorial recommendation | QA suggested 5.2 'after the stumble' point to E7g for the learning method; no such pointer is in E7a | Add a one-line pointer. Lead editor. |
| 37 | E7c | DC succession path not in the facts register | Editorial recommendation | 2.2 uses the Lodge DC Guide (Oct 2025) path: two years as ADC, three to five as DC, a year supporting his successor | Add it to the facts register. Lead editor. |
| 38 | E7c | Charity Governance Code wording (B16) | Editorial recommendation | Wording is qualified, but was checked only against secondary summaries | Check the current Code text. Lead editor. |
| 39 | E7g | Ceremony Explained series | Editorial recommendation | Removed because it was not found in the library; replaced by UGLE's degree guides and Solomon | Name it in 3.1 if it exists and is approved. Provincial Mentor. |
| 40 | E7h | B5 Royal Arch Mentoring Guide | Editorial recommendation | Not yet published; note kept in devNotes | Add a pointer when B5 is published. Lead editor. |

# Suitable for publication

| No. | Course(s) | Item | Classification | Why | Action and owner |
| --- | --- | --- | --- | --- | --- |
| 41 | All | Hub validation and build | Suitable for publication | All 167 lessons and 168 questions pass the Hub's validation (re-run on the final data, no problems); builder checks scenario routes, durations, feedback and dashes | None. Lead editor. |
| 42 | All | Contacts to check at every issue | Suitable for publication | Verified 26 October 2026: 999; NHS 111 option 2 in Hertfordshire; HPFT 0800 6444 101; Samaritans 116 123; Shout 85258; MCF 0800 035 60 90 and its name | Recheck at every issue, with the monthly call time, the dispensation fee, the Book of Constitutions edition and the Community Life Survey figure (E20). Lead editor. |
| 43 | All | Constitutional wording | Suitable for publication | Rules 183, 148, 127, 172, 105(a)/109, 115, 104(f), 146 follow the approved wordings; no Lodge-vote or 'Hermes Province' text remains | None. |
| 44 | All | Welfare and safety wording | Suitable for publication | E7f's model applied throughout: Almoner with his agreement, Lodge Mentor told only what he needs, no promise of absolute secrecy, 999 and NHS 111 option 2. E2's after-a-crisis line now matches E7f | None. |
| 45 | All | Unverified claims removed or attributed | Suitable for publication | Herts Initiate figures (D12), Mentor of the Year figure (D13), 'several Provinces' (D18), MENTOR two hours (E19), Solomon 'welcome material' (E08), etiquette figures (B14) | Reinstate D12 or D13 only if confirmed. Provincial Mentor. |
| 46 | All | Quiz feedback model | Suitable for publication | The Hub has no per-option feedback; every question has feedbackCorrect, feedbackIncorrect and an explanation covering each option | None. |
| 47 | All | Privacy in reflections and Lodge tasks | Suitable for publication | No prompt asks for names or circumstances of other Brethren; lists are made on paper in the Lodge | None. |
| 48 | E1, E2, E6, E7a, E7h | Royal Arch consistency | Suitable for publication | Four weeks after Raising; 'wait for the Chair' a myth in UGLE's words; 'fourth degree' only as a corrected error; Representative not called an officer | None. |

# Status by course

Blocking items are those classified Must resolve before publication. Confirmations are the Requires Provincial confirmation items that touch the course.

| Course | Overall status | Blocking items | Confirmations |
| --- | --- | --- | --- |
| E1 Lodge Mentor Essentials | Content ready, subject to approval of the Charge (7); blocked only by the Hub import changes and the nhs.uk check | 2, 3, 4, 5 | 6, 7, 9, 10, 11, 14, 18, 19 |
| E2 Personal Mentor Course | Content ready; blocked only by the Hub import changes and the nhs.uk check | 2, 3, 4, 5 | 6, 8, 9, 11, 18, 28, 29 |
| E6 The Chair and Beyond | Content ready; blocked only by the Hub import changes | 2, 3, 4 | 6, 10, 11, 14, 17, 19, 20, 24 |
| E7a The Mentoring Conversation | Content ready; blocked only by the Hub import changes and the nhs.uk check | 3, 4, 5 | 6, 12 |
| E7b Organising Mentoring in Your Lodge | Content ready; blocked only by the Hub import changes | 3, 4 | 6, 10, 12, 18, 27 |
| E7c Succession Planning | Content ready; blocked only by the Hub import changes | 3, 4 | 6, 12, 15, 16, 17 |
| E7d The First Two Years | Content ready; blocked only by the Hub import changes | 3, 4 | 6, 18, 26, 29 |
| E7e Keeping Good Men | Content ready; blocked only by the Hub import changes | 3, 4 | 6, 10, 11, 12, 14, 15, 19 |
| E7f Welfare, Wellbeing and Knowing Your Limits | Not ready: the safeguarding contact and policy must be named; also blocked by the Hub import changes and the nhs.uk check | 1, 3, 4, 5 | 6, 8, 12, 21 |
| E7g Helping Brethren Learn | Content ready; blocked only by the Hub import changes | 3, 4 | 6, 13, 25 |
| E7h One Journey | Content ready; blocked only by the Hub import changes | 3, 4 | 6, 22, 23, 30 |